## Slide 1: Take-Home Maglev Labs to Promote Self-Efficacy
Topic
  Development and assessment of a new type of personal lab for engineering students
Implementation roadmap
  January – June:
     Design and build a system
      V2.6 (working)
      V3.0 (finished design, in assembly)
     Produce learning material
      Book on the system by master’s students 
     Deploy simple control algorithms
      Implementations found in our GitHub repository
  June - July:
     Design our assessment method
  August:
     Execute a 2-day mini-course for students at IE
  Aug. – Sept.:
     Analyze and disseminate results
Outcomes
   Working system & teaching material
   Workshop & dissemination report
  Papers:
     IBCE24
     Maglev 2024
Kunnskap for ei betre verd
Date: 10.06.2024